## Detail plan Reduced Scope
| Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25
Who | 2012-03-26 | 2012-03-27 | 2012-03-28 | 2012-03-29 | 2012-03-30 | 2012-04-02 | 2012-04-03 | 2012-04-04 | 2012-04-05 | 2012-04-06 | 2012-04-09 | 2012-04-10 | 2012-04-11 | 2012-04-12 | 2012-04-13 | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-11 | 2012-06-12 | 2012-06-13 | 2012-06-14 | 2012-06-15 | 2012-06-18 | 2012-06-19 | 2012-06-20 | 2012-06-21 | 2012-06-22
Anders | [5 empty] | Buffer
Mikael | [6 empty] | US1: Setup project with GitHub and create structor | US1: Setup project with GitHub and create structor | US1: Setup project with GitHub and create structor | US4: Create Documentation | US4: Create Documentation | US4: Create Documentation | US4: Create Documentation | US4: Create Documentation | US4: Create Documentation | US4: Create Documentation | US5: Create Android template. | US5: Create Android template. | Scrum poker for estimate tasks | US6: Break down requirments | US6: Break down requirments | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US16: Class Owerview” Android/ClassDiagram | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US12: Använd OAUTH för att använda Google Docs som den påloggade användaren | US12: Använd OAUTH för att använda Google Docs som den påloggade användaren | US4: Documentation | US4: Documentation | TEST Android and Cloud app | TEST Android and Cloud app | Stablization | Stablization | TEST Cloud App | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US4: Documentation | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US4: Documentation | TEST Android and Cloud app | Stablization | Stablization | Go Live
Robin | [6 empty] | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US2: Make a mockup of Andriod App | US5: Create Android template. | US5: Create Android template. | Scrum poker for estimate tasks | US6: Break down requirments | US5: Create Android template. | US4: Documentation | US4: Documentation | US17: Setup baseproject, git structure for Android App | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | US15:Create /refactoring på Android login Android | US15:Create /refactoring på Android login Android | US15:Create /refactoring på Android login Android | TEST Android and Cloud app | TEST Android and Cloud app | Stablization | Stablization | Stablization | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US4: Documentation | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | TEST Android and Cloud app | US4: Documentation | TEST Android and Cloud app | TEST Android and Cloud app | Stablization | Go Live
Jesper | [6 empty] | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US3: Start working with the Cloud Studio App myApartments | US4: Create Documentation | US4: Create Documentation | Scrum poker for estimate tasks | US6: Break down requirments | US2: Make a mockup of Andriod App | US7: Mitt Nya Hem - Bostadsformulär | US9: Ta fram team i mittNyaHem | US11: Open Id inloggning via Android | US11: Open Id inloggning via Android | US11: Open Id inloggning via Android | US12: Använd OAUTH för att använda Google Docs som den påloggade användaren | US4: Documentation | US4: Documentation | US12: Använd OAUTH för att använda Google Docs som den påloggade användaren | TEST Android and Cloud app | TEST Android and Cloud app | Stablization | Stablization | TEST Cloud App | US14 :Create ”Base Android Activitys” Android | US14 :Create ”Base Android Activitys” Android | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US4: Documentation | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | TEST Android and Cloud app | TEST Android and Cloud app | Stablization | Go Live
Cloud App
Android
Documentation
Planning
Test

## Resource overview
Task/week | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Complete analysis | [15 empty] | Deliverable: | Go Live:
Cloud App | [15 empty] | Cloud App | 2012-05-27
Internal Test & Regression test |  |  |  |  | IT | [10 empty] | Android App | 2012-05-27
UAT | [5 empty] | UAT
Stabilization
Go Live with Cloud App | [9 empty] | 5/27
Android App
Internal Test | [7 empty] | IT
UAT | [8 empty] | UAT
Stabilization
Go Live | [9 empty] | 5/27
Documentation
Report bugs in Cloud AppStudio360
| W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
Analys | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20
Test |  | 0 | 30 |  | 30 | 37 | 10 | 30 | 30 |  |  |  |  | 167
Development |  | 80 | 80 | 90 | 80 | 73 | 100 | 80 | 70 |  |  |  |  | 653
Documentation |  | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  |  | 110
Deployment | W16: 10; W21: 10 |  |  | 20
Total |  | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 |  |  |  |  | 970
|  |  | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
Type | Name
Test | All |  | W15: 30; W17: 30; W18: 37; W19: 10; W20: 30; W21: 30 |  | 167
Developer 1 | Mikael |  | W15: 20; W16: 30; W18: 33; W19: 30; W20: 20; W21: 10 |  | 143
Developer 2 | Jesper |  |  | 40 | 30 | 30 | 40 | 30 | 30 | 30 | 30 |  |  |  | 260
Developer 3 | Robin |  |  | 40 | 30 | 30 | 40 | 10 | 40 | 30 | 30 |  |  |  | 250
Solution Architect | All |  | W13: 10; W16: 10 |  | 20
Deployment | All |  | W16: 10; W21: 10 |  | 20
Documentation | All |  |  | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 110
Total |  |  | 10 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 0 | 0 |  | 970