## Project Data
Projects Daily Log
Project Name: | Cloud App Studio
Date: | 2012-04-02
Author: | Mikael Floberg
Owner: | Mikael Floberg
Client: | Amantech

## Daily Log
Id. | Date of Entry | Prob, Act, Ev, Com | Description | Responsible | Target Date | Results | To be shared with Amantech Yes/No | Status
1 | 2012-04-02 | Action | Create "Project Daily Log" document | Mikael | 2012-04-04 |  | Yes | Closed
2 | 2012-04-02 | Action | Maintain "Project Daily Log" document | All | 2012-05-28 |  | Yes | Open
3 | 2012-04-02 | Action | Create" User Requirement Specification - Version 0 1" document | Mikael | 2012-04-04 |  | Yes | Closed
4 | 2012-04-02 | Action | Maintain" User Requirement Specification - Version 0 1" document | All | 2012-04-20 |  | Yes | Open
5 | 2012-04-02 | Action | Learn the enviorment | All | 2012-04-10 |  | Yes | Closed
6 | 2012-04-02 | Action | Create GitHub Repository | Mikael | 2012-04-04 |  | Yes | Closed
7 | 2012-04-02 | Action | Create "MinutesOfMeeting - w14" document | Mikael | 2012-04-04 |  | Yes | Closed
8 | 2012-04-02 | Action | Create "week14" documentation. | Mikael | 2012-04-04 |  | Yes | Closed
9 | 2012-04-10 | Action | Create "MinutesOfMeeting - w15.1" document | Mikael | 2012-04-11 |  | Yes | Closed
10 | 2012-04-10 | Action | Create "uppstart" documentation and upload it to HGO. | Mikael | 2012-04-11 |  | Yes | Closed
11 | 2012-04-10 | Event | Pass "Val av arbete och uppstart [26/3 - 1/4]" | All | 2012-04-01 |  | Yes | Closed
12 | 2012-04-10 | Action | Create "week15-16" documentation. | Mikael | 2012-04-11 |  | Yes | Closed
13 | 2012-04-10 | Action | Create "week17" documentation. | Mikael | 2012-04-11 |  | Yes | Closed
14 | 2012-04-10 | Action | Create Mockup for Android App | Robin | 2012-04-15 |  | Yes | Open
15 | 2012-04-10 | Action | Start working on the Cloud App mittNyaHem | Jesper | 2012-04-15 |  | Yes | Closed
16 | 2012-04-02 | Action | Fix the GitHub index start page: http://nero2000.github.com/Amantech | All | 2012-04-15 |  | Yes | Open
17 | 2012-04-10 | Event | Pass Sprint 1 [2/4 - 15/4] | All | 2012-04-15 |  | Yes | Open
18 | 2012-04-10 | Event | Pass Sprint 2 [16/4 - 29/4] | All | 2012-04-29 |  | Yes | Open
19 | 2012-04-10 | Event | Pass Sprint 3 [30/4 - 13/5] | All | 2012-05-13 |  | Yes | Open
20 | 2012-04-10 | Event | Pass Sprint 4 [14/5 - 27/5] | All | 2012-05-27 |  | Yes | Open
21 | 2012-04-10 | Event | Pass Avslut och redovisning [28/5 - 3/6] | All | 2012-06-03 |  | Yes | Open
22 | 2012-04-10 | Action | How does Cloud App Studio work? | All | 2012-06-03 |  | Yes | Open
23 | 2012-04-10 | Action | Create "project plan" document | Mikael | 2012-04-12 |  | Yes | Closed
24 | 2012-04-13 | Action | Create "MinutesOfMeeting - w15.2" document | Mikael | 2012-04-13 |  | Yes | Closed
25 | 2012-04-13 | Action | Create "Burndown Chart" document | Mikael | 2012-04-15 |  | Yes | Closed
26 | 2012-04-15 | Action | Create "MinutesOfMeeting - w15.3" document | Mikael | 2012-04-16 |  | Yes | Closed
70
71
72
73
74
75
76
77
78
79
80
81
82
83