## Detail plan Reduced Scope
| Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25
Who | time axis 2012-03-26 to 2012-06-22
Anders | 2012-04-02: Buffer
Mikael | 2012-04-03: US1: Setup project with GitHub and create structor; 2012-04-04: US1: Setup project with GitHub and create structor; 2012-04-05: US1: Setup project with GitHub and create structor; 2012-04-06: US4: Create Documentation; 2012-04-09: US4: Create Documentation; 2012-04-10: US4: Create Documentation; 2012-04-11: US4: Create Documentation; 2012-04-12: US4: Create Documentation; 2012-04-13: US4: Create Documentation
Robin | 2012-04-03: US2: Make a mockup of Andriod App; 2012-04-04: US2: Make a mockup of Andriod App; 2012-04-05: US2: Make a mockup of Andriod App; 2012-04-06: US2: Make a mockup of Andriod App; 2012-04-09: US2: Make a mockup of Andriod App; 2012-04-10: US2: Make a mockup of Andriod App; 2012-04-11: US2: Make a mockup of Andriod App; 2012-04-12: US2: Make a mockup of Andriod App; 2012-04-13: US2: Make a mockup of Andriod App
Jesper | 2012-04-03: US3: Start working with the Cloud Studio App myApartments; 2012-04-04: US3: Start working with the Cloud Studio App myApartments; 2012-04-05: US3: Start working with the Cloud Studio App myApartments; 2012-04-06: US3: Start working with the Cloud Studio App myApartments; 2012-04-09: US3: Start working with the Cloud Studio App myApartments; 2012-04-10: US3: Start working with the Cloud Studio App myApartments; 2012-04-11: US3: Start working with the Cloud Studio App myApartments; 2012-04-12: US3: Start working with the Cloud Studio App myApartments; 2012-04-13: US3: Start working with the Cloud Studio App myApartments

## Resource overview
Task/week | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Complete analysis | [15 empty] | Deliverable: | Go Live:
Cloud App | [15 empty] | Cloud App | 2012-04-20
Internal Test & Regression test |  |  |  | IT | [11 empty] | Android App | 2012-04-27
UAT |  |  |  |  | UAT
Stabilization
Go Live with Cloud App
Android App
Internal Test | [7 empty] | IT
UAT | [8 empty] | UAT
Stabilization
Go Live | [9 empty] | 3/7
Documentation
Report bugs in Cloud AppStudio360
| W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
Analys | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20
Test |  | 0 | 30 |  | 30 | 37 | 10 | 30 | 30 |  |  |  |  | 167
Development |  | 80 | 80 | 90 | 80 | 73 | 100 | 80 | 70 |  |  |  |  | 653
Documentation |  | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  |  | 110
Deployment | W16: 10; W21: 10 |  |  | 20
Total |  | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 |  |  |  |  | 970
|  |  | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23
Type | Name
Test | All |  | W15: 30; W17: 30; W18: 37; W19: 10; W20: 30; W21: 30 |  | 167
Developer 1 | Mikael |  | W15: 20; W16: 30; W18: 33; W19: 30; W20: 20; W21: 10 |  | 143
Developer 2 | Jesper |  |  | 40 | 30 | 30 | 40 | 30 | 30 | 30 | 30 |  |  |  | 260
Developer 3 | Robin |  |  | 40 | 30 | 30 | 40 | 10 | 40 | 30 | 30 |  |  |  | 250
Solution Architect | All |  | W13: 10; W16: 10 |  | 20
Deployment | All |  | W16: 10; W21: 10 |  | 20
Documentation | All |  |  | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | 110
Total |  |  | 10 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 0 | 0 |  | 970