## Project Data
Projects Daily Log
Project Name: | Cloud App Studio
Date: | 2012-04-02
Author: | Mikael Floberg
Owner: | Mikael Floberg
Client: | Amantech

## Daily Log
Id. | Date of Entry | Prob, Act, Ev, Com | Description | Responsible | Target Date | Results | To be shared with Amantech Yes/No | Status
1 | 2012-04-02 | Action | US1: Create "Project Daily Log" document | Mikael | 2012-04-04 |  | Yes | Closed
2 | 2012-04-02 | Action | US14: Maintain "Project Daily Log" document | All | 2012-05-28 |  | Yes | Open
3 | 2012-04-02 | Action | US1: Create" User Requirement Specification - Version 0 1" document | Mikael | 2012-04-04 |  | Yes | Closed
4 | 2012-04-02 | Action | US14: Maintain" User Requirement Specification - Version 0 1" document | All | 2012-04-20 |  | Yes | Open
5 | 2012-04-02 | Action | Learn the enviorment | All | 2012-04-10 |  | Yes | Closed
6 | 2012-04-02 | Action | US1: Create GitHub Repository | Mikael | 2012-04-04 |  | Yes | Closed
7 | 2012-04-02 | Action | US1: Create "MinutesOfMeeting - w14" document | Mikael | 2012-04-04 |  | Yes | Closed
8 | 2012-04-02 | Action | US1: Create "week14" documentation. | Mikael | 2012-04-04 |  | Yes | Closed
9 | 2012-04-10 | Action | US14: Create "MinutesOfMeeting - w15.1" document | Mikael | 2012-04-11 |  | Yes | Closed
10 | 2012-04-10 | Action | US1: Create "uppstart" documentation and upload it to HGO. | Mikael | 2012-04-11 |  | Yes | Closed
11 | 2012-04-10 | Event | Pass "Val av arbete och uppstart [26/3 - 1/4]" | All | 2012-04-01 |  | Yes | Closed
12 | 2012-04-10 | Action | US14: Create "week15-16" documentation. | Mikael | 2012-04-11 |  | Yes | Closed
13 | 2012-04-10 | Action | US14: Create "week17" documentation. | Mikael | 2012-04-11 |  | Yes | Closed
14 | 2012-04-10 | Action | US2: Create Mockup for Android App | Robin | 2012-04-15 |  | Yes | Closed
15 | 2012-04-10 | Action | US3: Start working on the Cloud App mittNyaHem | Jesper | 2012-04-15 |  | Yes | Closed
16 | 2012-04-02 | Action | US15: Fix the GitHub index start page: http://nero2000.github.com/Amantech | All | 2012-04-15 |  | Yes | Closed
17 | 2012-04-10 | Event | Pass Sprint 1 [2/4 - 15/4] | All | 2012-04-15 |  | Yes | Closed
18 | 2012-04-10 | Event | Pass Sprint 2 [16/4 - 29/4] | All | 2012-04-29 |  | Yes | Open
19 | 2012-04-10 | Event | Pass Sprint 3 [30/4 - 13/5] | All | 2012-05-13 |  | Yes | Open
20 | 2012-04-10 | Event | Pass Sprint 4 [14/5 - 27/5] | All | 2012-05-27 |  | Yes | Open
21 | 2012-04-10 | Event | Pass Avslut och redovisning [28/5 - 3/6] | All | 2012-06-03 |  | Yes | Open
22 | 2012-04-10 | Action | How does Cloud App Studio work? | All | 2012-06-03 |  | Yes | Open
23 | 2012-04-10 | Action | US14: Create "project plan" document | Mikael | 2012-04-12 |  | Yes | Closed
24 | 2012-04-13 | Action | US14: Create "MinutesOfMeeting - w15.2" document | Mikael | 2012-04-13 |  | Yes | Closed
25 | 2012-04-13 | Action | US1: Create "Burndown Chart" document | Mikael | 2012-04-15 |  | Yes | Closed
26 | 2012-04-15 | Action | US14: Create "MinutesOfMeeting - w15.3" document | Mikael | 2012-04-16 |  | Yes | Closed
27 | 2012-04-16 | Action | US14: Create "MinutesOfMeeting - w15.4" document | Jesper | 2012-04-17 |  | Yes | Closed
28 | 2012-04-18 | Action | US14: Create "MinutesOfMeeting - w15.5" document | Robin | 2012-04-19 |  | Yes | Closed
29 | 2012-04-18 | Action | US14: Documentation update | Mikael | 2012-04-19 |  | Yes | Closed
30
31 | 2012-04-18 | Action | US5: Create Android template | Robin | 2012-04-23 |  | Yes | Open
32 | 2012-04-18 | Action | US7: Ta fram grundformen för mittNyaHem | Jesper | 2012-04-23 |  | Yes | Open
33 | 2012-04-18 | Action | Scrum poker planning | All | 2012-04-19 |  | Yes | Closed
34 | 2012-04-18 | Action | US6: Break down requirments | All | 2012-04-20 |  | Yes | Open
35 | 2012-04-18 | Action | Us8: Ta fram sorterbar vy för bostäder i mittNyaHem | All |  |  | Yes | Open
36 | 2012-04-18 | Action | US9: Ta fram team i mittNyaHem | All |  |  | Yes | Open
37 | 2012-04-18 | Action | US10: Utveckla en native Androidapp som konsumerar och visar information från Mitt Nya Hem. | All | 2012-05-10 |  | Yes | Open
38 | 2012-04-18 | Action | US11: Open Id inloggning via Android | All | 2012-05-04 |  | Yes | Open
39 | 2012-04-18 | Action | US12: Använd OAUTH för att använda Google Docs som den påloggade användaren | All | 2012-05-22 |  | Yes | Open
40 | 2012-04-18 | Action | US13: Skapa en Cloud App Studio app anpassad för Apple Retina skärmar | All | 2012-05-18 |  | Yes | Open
41 | 2012-04-19 | Action | US17: Setup baseproject, git structure for Android App | Robin | 2012-04-26 |  | Yes | Closed
42 | 2012-04-29 | Action | US14 :Create ”Base Android Activitys” Android | Jesper | 2012-05-15 |  | Yes | Open
43 | 2012-04-29 | Action | US15:Create /refactoring på Android login Android | Robin | 2012-05-04 |  | Yes | Open
44 | 2012-04-29 | Action | US16:Create ”Class Owerview” Android/ClassDiagram | Mikael | 2012-04-26 |  | Yes | Closed
70
71
72
73
74
75
76
77
78
79
80
81
82
83